## Slide 1: Cost Management

## Slide 2: Outline
Cost estimation: up-down versus top-down
Item based budget versus activity based budget
Cumulative time-cumulative cost curve (S curve)

## Slide 3: Cost estimation: up-down versus top-down
Scope of work
Work Break Down Structure
Top down approach: set by the donor or top management
Bottom up approach: ask for price quotations

## Slide 4: Item based budget versus activity based budget
Example: A training project (activities: A, B, C)
- Project duration: 6 days (1 day is preparation (A) + 4-day training (B)+ 1 day field visit (C))
1 2 3 4 5 6
A
B
C

## Slide 5: Item based budget versus activity based budget
Item | Description | Cost (USD)
Personnel | Trainer | 4000 (1000 per day)
Equipment | Laptop LCD | 1000 (at the beginning) 500 (at the beginning)
Training materials | Printing | 500 (at the beginning)
Field visit | Visiting a project | 500 (at the end)
 |  | 6500
ITEM BASED BUDGET

## Slide 6: Item based budget versus activity based budget
Activity | Description | Budget (USD) | 
Day 1 | Buy laptop Buy LCD Printing out | 1000 500 500 | 2000
Day 2 | Training | 1000 | 1000
Day 3 | Training | 1000 | 1000
Day 4 | Training | 1000 | 1000
Day 5 | Training | 1000 | 1000
Day 6 | Field visit | 500 | 500
 |  |  | 6500

## Slide 7: Cumulative time-cumulative cost curve (S curve)
1 2 3 4 5 6
A
B
C
2000 1000 1000 1000 1000 500
Laptop
LCD
Printing
Field visit
Training
2000 3000 4000 5000 6000 6500
Cost per day
Cumulative cost

## Slide 8: S Curve
1 2 3 4 5 6
1000
2000
3000
4000
5000
6000
6500