- A network consists of the following list. Times are given in weeks.

| Activity | Preceding | Duration |
| --- | --- | --- |
| A | -- | 9 |
| B | A | 2 |
| C | A | 12 |
| D | A | 5 |
| E | B | 6 |
| F | B | 8 |
| G | C, F | 3 |
| H | D | 2 |
| I | H | 8 |
| J | G, I | 6 |
| K | E, J | 2 |

a. 	Draw the network diagram.

b. 	Which activities form the critical path?

c. 	How much slack exists at activities A and F?

d. 	What is the duration of the critical path?

(a) Network diagram

(b) paths A-D-H-I-J-K and A-C-G-J-K are critical; (c) A has no slack; F has 2 units (d) 32

- A partially solved PERT problem is detailed in the table below. Times are given in weeks.

| Activity | Preceding | Optimistic Time | Probable Time | Pessimistic Time | Expected Time | Variance |
| --- | --- | --- | --- | --- | --- | --- |
| A | -- | 7 | 9 | 14 |  |  |
| B | A | 2 | 2 | 8 |  |  |
| C | A | 8 | 12 | 16 |  |  |
| D | A | 3 | 5 | 10 |  |  |
| E | B | 4 | 6 | 8 |  |  |
| F | B | 6 | 8 | 10 |  |  |
| G | C, F | 2 | 3 | 4 |  |  |
| H | D | 2 | 2 | 8 |  |  |
| I | H | 6 | 8 | 16 |  |  |
| J | G, I | 4 | 6 | 14 |  |  |
| K | E, J | 2 | 2 | 5 |  |  |

a.	Calculate the expected time for each activity. Enter these values in the appropriate column in the table above.

b. 	Which activities form the critical path?

c. 	What is the estimated time of the critical path?

d.  	What are the project variance and the project standard deviation?

e. 	What is the probability of completion of the project after week 40?

(a) A=9.5 B=3 C=12 D=5.5 E=6 F=8 G=3 H=3 I=9 J=7 K=2.5 
(b) A-D-H-I-J-K; (c) 36.5; (d) 9.53, 3.09; (e) 0.13.